## Cover Page
Question Paper Generator System
Product Backlog
74
|  | Prepared By / Last Updated By | Reviewed By | Approved By
| Name | Person 3
| Role | Product Owner
Signature
Date
Project ID: Gauge Your Knowledge |  |  |  | <SCI.ID> / Ver: <No.>
Release ID: QTAD-PBL / 2.0.0 / 30-Mar-2015 |  |  |  | C3: Protected
Controlled copy
Controlled copy
Controlled copy
Controlled Copy

## Instructions
Product Backlog - Instructions Question Paper Generator System Release ID: QTAD-PBL / 2.0.0 / 30-Mar-2015 C3: Protected Controlled Copy Project ID: Gauge Your Knowledge <SCI.ID> / Ver: <No.>
Product Backlog Worksheet
This sheet has to be filled while doing "Create Product Backlog" task in the Initial Envisioning Phase.
Fill the following fields in the product backlog worksheet for each feature set
| Sl.No | <Provide the Serial number for each product backlog item>
| Feature Set/ Requirements ID | <Provide unique ID for each feature set/ requirement>
| Short Description of Feature Set/ Feature | < Provide a short description of the Feature set/ Feature>. A “Feature” is a small client valued functionality. A Feature set is a grouping of business-related features.
| Dependency of Feature Set/ Feature | <Provide the Dependency between the feature sets/ features>
| Feature Owner | <Name the person(s) responsible for providing detailed information / clarifications on the Feature Set/ Requirements>.
| Feature Complexity | <Classify the complexity of Feature Set/ Feature in terms of Trivial, Simple, Average, Complex>
| Business Priority | <Provide the business priority of the Feature Set/ Feature in terms of Low, Medium, High>
| Feature Type | <Classify the Feature Set/ Feature as New Requirement, Enhancement, Bug, Issue>
| Remarks | <Provide the remarks/ comments for the feature set/ Feature`>. E.g. Describe the assumptions made on the feature sets, its constraints, etc
Product Backlog Release Tracking Worksheet
The Product backlog worksheet contains a list of everything (Features, known issues, bugs etc) that the business would want to implement in an application. This worksheet would continue to exist from the beginning to the end of the project. The Product Owner maintains it by adding, modifying, removing any of the items listed there. They can also change the priority of the items so long as they are not being worked by the team in the ongoing Sprint. Most of the re-ordering would happen just before the Sprint Planning meeting. To ensure this kind of continuous update, this worksheet could be re-visited during periodic intervals once during the release elaboration Phase and thereafter during the project execution. The changes to the Product backlog could be triggered from several sources in terms of inclusion of new features / bugs/ known issues based on the stakeholder requests and the effort, schedule for the same would also be re-visited in the product backlog worksheet.
| Release Iteration # | <Provide the release iteration number>
| Release Start Date | <Provide the estimated start date of each Release>
| Release End Date | <Provide the estimated end date of each Release>
| Estimated Effort for Release (person days) | <Provide the estimated effort in person days for each Release>
| Team Size For Release | <List the number of team members required for the release>
| Estimated Velocity For Release (FCP/Features) | <Provide the estimated velocity by specifying the feature complexity points/no of features that can be delivered at the end of a release.>
| Feature Set ID | <From the Product Backlog worksheet, list the Feature Set IDs that are scoped in the corresponding release Iteration #>
| Feature ID | <Provide unique ID for each feature /requirement>
| Feature Name | <Name the features that are identified and scoped in the corresponding release Iteration #>
| Dependency of Feature | <Provide the Dependency between features>
| Original Scope | <Assign a symbol “X” if a feature is identified as part of the product backlog prior to the commencement of a release> This field would not be updated for new feature additions that are identified during the release execution (i.e. after baselining the product backlog). In such a scenario, this field would be blank thereby indicating that this feature has been newly added for a release. Additionally this field would be considered for calculating the burn down (person days completed) for original set of features. This field would aid in differentiating the originally scoped features Vs the newly scoped features for plotting the release burn down chart.
| Planned Sprint Iteration # | Once the features are assigned to a release, the next logical step would be to map these features to multiple sprint iterations. To enable this mapping, the user needs to update this field 'Planned Sprint Iteration #' for the set of features that would be logically grouped within this sprint iteration. Note: However the allocation of features to sprint iteration might change as per the stakeholder priorities, technical constraints, etc while doing the sprint planning activity during the sprint zero/ execution phase
| Initial Estimate For Feature (person days) | <Provide the initial estimated effort (in person days) for each feature> This initial estimate value would be updated first irrespective of whether it is an originally scoped feature/ or a newly scoped feature that is being added during the course of the project. In case there is a scope change, the team would need to re-visit the effort for these features (original or newly scoped features) and update the revised effort in the “revised estimate for a feature” field. Additionally if there is no scope change, the same value as entered in the Initial estimate would be reflected in the “revised estimate“ field as well. Basically the revised estimated would always be considered for the release burn down chart as we can include only a single data source to represent the graph.
| Revised Estimate For Feature (person days) | <Provide the Revised estimated effort (in person days) for each feature> The size/or the effort for the original set of features/ or for the newly scoped features could be re-visited for the following scenarios :- a) Scope changes for the existing/ or the newly added features could be triggered based on stakeholder inputs b) Based on the effort expended for the completed features as on date, the effort could be re-visited for downstream features Note: The revised estimate value would be considered for the following purposes:- a) For computing the total effort for the project (in person days) b) For computing the Release burn down chart
| Feature Status | Once the feature is identified and taken forward for implementation, the feature could be represented through several statuses thereby indicating the current status of implementation. <Refer below for details on different feature status> Proposed – A feature is identified, but not yet scoped for a release/ sprint iteration. Assigned – The identified features are allocated to a release/ sprint iteration Start - The assigned feature is initiated for implementation Complete – A feature is said to be complete when it has been developed, tested, and delivered to the customer Re-Assigned – A feature could be re-assigned to a subsequent sprint or release iteration in case of backlogs from earlier sprints. Hold - The feature might be put on hold due to certain constraints/ stakeholder's request, etc Cancelled - A feature is cancelled or removed from scope of the release/ sprint Note: The above feature status field would be considered for computing the following scenarios:- a) To calculate the completed work (in person days) for originally scoped feature b) To calculate the remaining hours (in person days) available for completing newly scoped feature. c) To calculate the completed work (in person days) for newly scoped feature
Calculated Fields
| Original Features - Completed (person days) | This value is non editable. This field would aid in calculating the burn down for original set of scoped features. If the feature is mapped as 'X' (originally scoped for a release) and the feature status is marked as "complete", the revised effort depicted in column 'N' for that feature is auto populated in this field.
| New Features - Not Completed (person days) | This value is non editable. This field would aid in calculating the effort required to complete the remaining work for the newly scoped features. If the original scope column is 'blank' for a feature and the status for same is not marked as "complete", the revised effort depicted in column 'N' for that feature is auto populated in this field.
| New Features - Completed (person days) | This value is non editable. This field would aid in calculating the burn down for the newly scoped features that are delivered to the customer. If the original scope column is 'blank' for a feature and the status for same is marked as "complete", the revised effort depicted in column 'N' for that feature is auto populated in this field.
Report Data Worksheet
The Report Data worksheet would form an input for plotting the release burn down chart and the "Effort By Iteration" chart. The Report Data worksheet would automatically populate the following data from "Product - Release Tracking" worksheet for each release iteration. 'Assigned' - This value indicates the amount of work(in person days) planned for each release iteration 'Work Remaining' - This field would indicate the remaining person days available to complete the release Iteration. The original as well as the new features are considered for computing this value. 'Original Features -Completed ( person days)' - This value would be computed as the cumulative sum of all the completed effort (in person days) as displayed in the "Burn-down (Original Features Completed)' field from the "Product - Release Tracking" worksheet. 'New Features - Not Completed (person days)' - This value would be computed as the cumulative sum of all the remaining effort in person days as displayed in the 'New Features (Not Completed)' field from the "Product - Release Tracking" worksheet. 'New Features - Completed (person days)' - This value would be computed as the cumulative sum of all the completed effort (in person days) as displayed in the "New Features (Completed)' field from the "Product - Release Tracking" worksheet. In this Report Data worksheet, the sample data for three release iterations are depicted. If a user needs to update a new release iteration number, the following needs to be done:- a) The user needs to include a new release iteration number in the column 'Release iteration #' as part of the "Product - Release Tracking" worksheet b) The second step would be to insert new rows (depending on the number of release iterations) at the end of the third release iteration row c) The third step would be to extend the formula embedded as part of "report data" worksheet to the subsequent newly inserted rows d) The fourth step would be to extend the source data range for the "Release Burn Down Chart" & "Effort By Iteration Chart" to depict the newly added release iterations. Note: There could the scenarios when new features are being identified, but are not being assigned to any release iterations in the product backlog. In such cases, the effort estimation for those features would be auto populated from "Product - Release Tracking" worksheet under the category "Not Assigned" to the Report Data worksheet. This would aid in identifying the unassigned features and enable the team to assign such features for subsequent releases.
Release Burn Down Chart
1. A typical release Burn Down chart would enable the Product Owner to assess as to how each iteration is progressing towards realizing the release goal. They would be able to assess the number of features that are going to make it (or) not make it to the release based on the number of features delivered by the team in each iteration. 2. Based on the progress being made by the team, the Product Owner may decide to add more Sprints within a release (if it is a feature driven release) or cut down some of the features from the Release backlog (if it is a Date driven release). The release burn down chart would be automatically plotted based on the data depicted in the "Report Data" worksheet. The release burn down graph highlights the progress of work being made across releases. The labels that are used to indicate the progress of work are elaborated below:- 'Work Remaining' - This label is represented by red color. It indicates the remaining person days available to complete the release Iteration. The original as well as the new features are considered for computing this value. 'Original Features -Completed ( person days)' - This label is represented by green color. It represents the cumulative sum of all the completed effort (in person days). 'New Features - Not Completed (person days)' - This label is represented by purple color. It indicates the cumulative sum of all the remaining effort in person days for the newly scoped features. 'New Features -Completed (person days)' - This label is represented by blue color. It indicates the cumulative sum of all the completed effort (in person days) for the newly scoped features. Interpretation of the Graph:- X axis : Release Iteration Number Y axis : Estimated Effort in Person Days for all the four labels
Effort By Iteration Chart
The "Effort By Iteration" pie chart depicts the percentage of effort (in person days) that is being consumed across various release iterations Vs the total project effort. This would aid the project team to assess the average effort expended across releases and predict the future release velocity based on the historical data. Additionally this chart also highlights the percentage of features that are not yet assigned to any release. Based on the current release velocity, the team could use this data to assign pending features in the current / or subsequent release iterations. Note: The source data for this chart has to be manually extended/ adjusted depending on the number of release iterations that are included in the "Report Data" worksheet.
Weighted Shortest Job First Technique (WSJF)
WSJF - Prioritizing features based on economics of development. Jobs that can deliver most value (CoD) and are shortest duration are selected first for implementation WSJF (Weighted Shortest Job First) = CoD/Duration CoD - opportunity cost to delay implementation of some functionality CoD is again made of 3 components namely User value , Time Value and Risk Reduction or Opportunity Enablement User value - Is simply the potential value of the feature in the eyes of the user Time value - is another relative estimate; one based on how the user value decays over time Risk Reduction or Opportunity Enablement -The risk reduction or unlocked potential of business opportunities that may be lost or gained based on delaying the release of functionality. Duration can be in hours/days/size For CoD and Duration, Fibonacci series (relative rating can be used)

## Product Backlog
Product Backlog - Product Backlog Question Paper Generator System Release ID: QTAD-PBL / 2.0.0 / 30-Mar-2015 C3: Protected Controlled Copy Project ID: Gauge Your Knowledge <SCI.ID> / Ver: <No.>
Sl.No | Feature Set / Requirements ID | Short Description of Feature Set/ Feature | Dependency of Feature Set/ Feature | Feature Owner | Feature Complexity | Business Priority | Feature Type | Remarks
1 | FS_1 / Req_1 to Req_2 | The objective of this requirement is to allow the user to Register/ login as User / Admin. | No dependency | Scrum Master | Average | High | New Requirement
2 | FS_2 / Req_3 | The objective of this requirement is to allow Super Admin to approve / deny admin registration | Has a dependency with FS_1 | Scrum Master | Average | High | New Requirement
3 | FS_3 / Req_4, Req_8 | The objective of this requirement is to allow Admin to add / update Exam details. | Has a dependency with FS_1, FS_2 | Scrum Master | Average | High | New Requirement
4 | FS_4 / Req_5, Req_9 | The objective of this requirement is to allow the Admin to upload the questions and Answers based on Skills and Difficulty level. Admin should be able to update the existing question answers. | Has a dependency with FS_1, FS_2, FS_3 | Scrum Master | Average | High | New Requirement
6 | FS_5 / Req_6 | The objective of this requirement is to allow the user to take assesment. | Has a dependency with FS_1, FS_2, FS_3, FS_4, FS_6 | Scrum Master | Average | High | New Requirement
7 | FS_6 / Req_7 | The objective of this requirement is to allow the system to generate question for the Test. | Has a dependency with FS_1, FS_2, FS_3, FS_4 | Scrum Master | Average | High | New Requirement
8 | FS_7 / Req_10 | Thie objective of this requirement is to allow the system to evaluate the assesment and update the result. | Has a dependency with FS_1, FS_2, FS_3, FS_4, FS_5, FS_6 | Scrum Master | Average | High | New Requirement
9 | FS_8 / Req_11 | Thie objective of this requirement is to allow the user to view the assesment report. | Has a dependency with FS_1, FS_2, FS_3, FS_4, FS_5, FS_6, FS_7 | Scrum Master | Average | High | New Requirement
10 | FS_9 / Req_12 | The objective of this requirement is to allow Admin to generate report on the Assessments available, Assessment taken, Pass percentage. | Has a dependency with FS_1, FS_2, FS_3, FS_4, FS_5, FS_6, FS_7 | Scrum Master | Average | High | New Requirement
11 | FS_10 / Req_13 | The objective of this requirement is to allow the graphical representation based on the skills and performance | Has a dependency with FS_1, FS_2, FS_3, FS_4, FS_5, FS_6, FS_7 | Scrum Master | Average | High | New Requirement
12 | FS_11 / Req_14 | The objective of this requirement is to allow customer to get other validations like forget user id, password | Has a dependency with FS_1 | Scrum Master | Average | High | New Requirement
13 | FS_12 / Req_15, Req_16 | The objective of this requirement is to allow customer to provide reviews, admin to update review questions, system to trigger for review | Has a dependency with FS_1, FS_2, FS_3 | Scrum Master | Average | High | New Requirement
14 | FS_13 / Req_17 | The objective of this requirement is to allow the user to Log off upon completion of the required activity | Has a dependency with FS_1 | Scrum Master | Average | High | New Requirement

## Product - Release Tracking
Product Backlog - Product - Release Tracking Question Paper Generator System Release ID: QTAD-PBL / 2.0.0 / 30-Mar-2015 C3: Protected Controlled Copy Project ID: Gauge Your Knowledge <SCI.ID> / Ver: <No.>
Release Iteration # | Release Start Date | Release End Date | Estimated Effort for Release (person days) | Team Size For Release | Estimated Velocity For Release (FCP/Features) | Feature Set ID | Feature ID | Feature Name | Dependency of Feature | Original Scope | Planned Sprint Iteration # | Initial Estimate For Feature (person days) | Revised Estimate For Feature (person days) | Feature Status | Calculated Fields
[15 empty] | Original Features - Completed (person days) | New Features - Not Completed (person days) | New Features -Completed (person days)
1 | TBU | TBU | TBU | 4 | TBU | FS_1 | FEA_1.1 | User Registration | User being able to enter the mandatory details and Register himself for accessing the system | X | TBU | TBU | TBU | Proposed | 0 | 0 | 0
2 | TBU | TBU | TBU | 4 | TBU | FS_1 | FEA_1.2 | User Authentication | The details entered by the User being authenticated and confirmed on the registration. | X | TBU | TBU | TBU | Proposed | 0 | 0 | 0
3 | TBU | TBU | TBU | 4 | TBU | FS_1 | FEA_1.3 | Admin Registration | Admin being able to enter the mandatory details and Register himself for accessing the system | X | TBU | TBU | TBU | Proposed | 0 | 0 | 0
4 | TBU | TBU | TBU | 4 | TBU | FS_1 | FEA_1.4 | Admin Authentication | The details entered by the Admin being authenticated and confirmed on the registration. | X | TBU | TBU | TBU | Proposed | 0 | 0 | 0
5 | TBU | TBU | TBU | 4 | TBU | FS_2 | FEA_2.1 | Admin registration approval | Super admin being able to approve / deny Admin registration | X | TBU | TBU | TBU | Proposed | 0 | 0 | 0
6 | TBU | TBU | TBU | 4 | TBU | FS_3 | FEA_3.1 | Add Exam Details | Admin being able to add the details of the Exam. | X | TBU | TBU | TBU | Proposed | 0 | 0 | 0
7 | TBU | TBU | TBU | 4 | TBU | FS_3 | FEA_3.2 | Add Competency Details | Admin being able to add the details of the Competency | X | TBU | TBU | TBU | Proposed | 0 | 0 | 0
8 | TBU | TBU | TBU | 4 | TBU | FS_3 | FEA_3.3 | Update Exam Details | Admin being able to update / maintain the details of the Exam added already. | X | TBU | TBU | TBU | Proposed | 0 | 0 | 0
9 | TBU | TBU | TBU | 4 | TBU | FS_3 | FEA_3.4 | Update Competency Details | Admin being able to update / maintain the details of the Competency added already. | X | TBU | TBU | TBU | Proposed | 0 | 0 | 0
10 | TBU | TBU | TBU | 4 | TBU | FS_4 | FEA_4.1 | Upload Questions | Admin being able to upload Questions based on the Skills and Difficulty level | X | TBU | TBU | TBU | Proposed | 0 | 0 | 0
11 | TBU | TBU | TBU | 4 | TBU | FS_4 | FEA_4.2 | Upload Multiple choices | Admin being able to upload the Multiple choice answers for the questions. | X | TBU | TBU | TBU | Proposed | 0 | 0 | 0
12 | TBU | TBU | TBU | 4 | TBU | FS_4 | FEA_4.3 | Update Questions | Admin being able to update / delete the questions and the answers present in the database | X | TBU | TBU | TBU | Proposed | 0 | 0 | 0
13 | [5 empty] | FS_5 | FEA_5.1 | Take assessment | User being able to take assesment | X | TBU | TBU | TBU | Proposed | 0 | 0 | 0
14 | TBU | TBU | TBU | 4 | TBU | FS_6 | FEA_6.1 | Question generation / Test conduction | System being able to pick up questions from the pool based on Competency and the diffculty level | X | TBU | TBU | TBU | Proposed | 0 | 0 | 0
15 | TBU | TBU | TBU | 4 | TBU | FS_6 | FEA_6.2 | Highlight Marked and Unmarked questions | System being able to highlight the marked and unmarked questions. It should also highlight answered and unanswered questions. | X | TBU | TBU | TBU | Proposed | 0 | 0 | 0
16 | TBU | TBU | TBU | 4 | TBU | FS_6 | FEA_6.3 | Answer verification and marking | System being able to verify the answers and award marks accordingly | X | TBU | TBU | TBU | Proposed | 0 | 0 | 0
17 | TBU | TBU | TBU | 4 | TBU | FS_6 | FEA_6.4 | Status update | Based on the marks gained, update the completion status. | X | TBU | TBU | TBU | Proposed | 0 | 0 | 0
18 | TBU | TBU | TBU | 4 | TBU | FS_7 | FEA_7.1 | Evaluate the assessment | System being able to evaluate the assesment | X | TBU | TBU | TBU | Proposed | 0 | 0 | 0
19 | TBU | TBU | TBU | 4 | TBU | FS_8 | FEA_8.1 | Assessment report | System being able to generate assesment report | X | TBU | TBU | TBU | Proposed | 0 | 0 | 0
20 | TBU | TBU | TBU | 4 | TBU | FS_9 | FEA_9.1 | Report generation | Admin being able to generate report of the Exam and the completion status | X | TBU | TBU | TBU | Proposed | 0 | 0 | 0
21 | TBU | TBU | TBU | 4 | TBU | FS_10 | FEA_10.1 | Graphical representation | Sytem being able to graphically represent the hierarchy of the topics included in a particular skill | X | TBU | TBU | TBU | Proposed | 0 | 0 | 0
22 | TBU | TBU | TBU | 4 | TBU | FS_11 | FEA_11.1 | Other validations | Customer being able to get other validations like forget user id, password | X | TBU | TBU | TBU | Proposed | 0 | 0 | 0
23 | TBU | TBU | TBU | 4 | TBU | FS_12 | FEA_12.1 | User Feedback | Customer being able to provide feedback | X | TBU | TBU | TBU | Proposed | 0 | 0 | 0
24 | TBU | TBU | TBU | 4 | TBU | FS_12 | FEA_12.2 | Add Feedback form | Admin being able to update feedback questions | X | TBU | TBU | TBU | Proposed | 0 | 0 | 0
25 | TBU | TBU | TBU | 4 | TBU | FS_13 | FEA_7.1 | Log off | Supplier / Admin being able to Log off after performing the required task. | X | TBU | TBU | TBU | Proposed | 0 | 0 | 0
[11 empty] | Total Effort For the Project (in Person Days) |  | 0
Legend
Read Only

## Report Data
Product Backlog - Report Data Question Paper Generator System Release ID: QTAD-PBL / 2.0.0 / 30-Mar-2015 C3: Protected Controlled Copy Project ID: Gauge Your Knowledge <SCI.ID> / Ver: <No.>
Effort By Release Iteration
Name |  | Assigned | Work Remaining | Original Features -Completed ( person days) | New Features - Not Completed (person days) | New Features -Completed (person days)
Release 1 | 1 | 28 | #REF! | 0 | 0 | 0
Release 2 | 2 | 40 | #REF! | 0 | 0 | 0
Release 0 | 0 | 0 | #REF! | 0 | 0 | 0
Not Assigned |  | 0 | #REF! | 0 | 0 | 0
Note on B7: In order to indicate the end of all release iteration, leave this one as ="". Otherwise, it won't calculate the non-assigned iterations properly.

## WSJF Technique
Product Backlog - WSJF Technique Question Paper Generator System Release ID: QTAD-PBL / 2.0.0 / 30-Mar-2015 C3: Protected Controlled Copy Project ID: <Project ID> <SCI.ID> / Ver: <No.>
CoD (Cost of Delay)
Feature | User/Business Value | Time Criticality | Risk Reduction or Opportunity Enablement | Total | Duration (Hours/Days/Size) | WSJF (CoD/Duration) | Priority
1 | 4 | 8 | 8 | 20 | 4 | 5 | 1
2 | 8 | 4 | 3 | 15 | 6 | 2.5 | 3
3 | 6 | 6 | 6 | 18 | 5 | 3.6 | 2

## Change Log
Change Log
Please note that this table needs to be maintained even if a Configuration Management tool is used.
Version Number | Changes Made
V1.0 | Initial baseline created on <dd-Mon-yy> by <Name of Author>
V 1.1 | Page No. | Changed By | Effective Date | Changes Effected
V 1.2 | Page No. | Changed By | Effective Date | Changes Effected